# PROJECT PLAN DOCUMENT

# Version -2

| Project number | 49 |
| --- | --- |
| Project Title | Social Venture Partner – Engagement Analytics Dashboard |
| Document | Project Plan |
| Creation date | 12/02/2026 |
| Modification date | 6/03/2026 (v2) |
| Created By | Athmeeya M Kashyap, Yogansh |
| Modified By | Navneet, Sambhavi |
| Client | Mr. Raja Poladi, CDiTH (IIITH – Internal) |

# Brief problem statement

Social Venture Partners (SVP) India manages a large network of partners engaged with numerous non-profit organizations through mentorship, financial contributions, volunteering, and strategic advisory. Currently, SVP relies on fragmented tools like NotebookLM and Excel spreadsheets, which limits their ability to analyse participation patterns, identify collaboration opportunities, and derive meaningful insights. The objective is to develop a comprehensive Engagement Analytics Dashboard that consolidates partner management and analytics into a unified platform with intuitive visualizations, enabling data-driven decision-making to enhance partner participation, strengthen NGO collaborations, and maximize philanthropic impact.

# Team Members

Athmeeya Kashyap      - 2024113015 - > Frontend (UI/UX Designer)

Navneet Gupta	- 2024111030 - > Backend (Database Administrator)

Prashant Vinod	- 2024101116 - > Frontend (Coordinator & Analytics)

Sambhavi Singh	- 2024117010 - > Backend (Backend Developer)

Yogansh Somisetty       - 2024101006 - > Frontend (Frontend Developer)

# Team Communication

The team will conduct regular meetings and maintain communication through the following channels:

- Weekly Team Meetings: Every Wednesday at 8:00 PM for project status updates, milestone review, and sprint planning.

- Communication Tools: The team will use WhatsApp and Microsoft Teams for daily communication, GitHub for code collaboration and version control.

- Client Meetings: Weekly meetings with Mr. Raja Poladi on Wednesdays to demonstrate progress and gather feedback.

# Development Environment

The project will utilize the following tools and technologies:

- Development IDE: Visual Studio Code with relevant extensions for JavaScript, Python, and database management with copilot for agentic coding.

- Frontend Framework: React.js for building the interactive dashboard interface with responsive design.

- Backend Framework: Node.js with Express.js for API development and server-side logic.

- Database: PostgreSQL for structured data storage.

- Version Control: Git and GitHub for source code management and collaborative development.

- Data Visualization: Chart.js and D3.js for creating interactive charts and analytics visualizations. [ Still to decide]

- Documentation: Swagger for API documentation.

- Deployment: AWS for cloud hosting. [ Still to Decide]

Milestone Schedule

| Milestone | Due Date | Release | Deliverable? |
| --- | --- | --- | --- |
| Conduct initial client meetings and problem understanding | 21/01/2026 | R1 | No |
| Complete backend research and engagement dashboard analysis | 21/01/2026 | R1 | No |
| Submit Project Synopsis document | 26/01/2026 | R1 | Yes |
| Create draft requirements | 28/01/2026 | R1 | No |
| Setup Git repository and communication channels | 28/01/2026 | R1 | No |
| Finalize software requirements document (SRS) | 04/02/2026 | R1 | Yes |
| Database schema design and setup | 04/02/2026 | R1 | No |
| Complete system architecture design and technology stack selection | 04/02/2026 | R1 | Yes |
| UI/UX Prototypes | 04/02/2026 | R1 | No |
| Configure Swagger APIs documentation | 11/02/2026 | R1 | Yes |
| Design database schema and set up PostgreSQL database. | 17/02/2026 | R1 | No |
| Implement backend for R1. | 28/02/2026 | R1 | Yes |
| Implement frontend for R1. | 7/03/2026 | R1 | Yes |
| Integrate backend and frontend and make R1 system. | 12/03/2026 | R1 | Yes |
| Conduct System Testing for all R1 core functionalities. | 17/03/2026 | R1 | Yes |
| Deploy R1 to cloud hosting, hand over to the client, and begin observation phase. | 18/03/2026 | R1 | No |
| Restart SDLC: Conduct requirements elicitation for R2 analytics and partner portal features. | 22/03/2026 | R2 | No |
| Detailed design for analytics and additional Partner features(SRS) | 28/03/2026 | R2 | Yes |
| Implement the Analytics views. | 1/04/2026 | R2 | Yes |
| Implement all the partner features. | 5/04/2026 | R2 | Yes |
| Implement all the feedback from R1 feedback | 5/04/026 | R2 | Yes |
| System acceptance testing and deployment of Analytics views | 10/04/2026 | R2 | Yes |
| System acceptance testing and deployment of Parner Portal features and R1 feedback | 15/04/2026 | R2 | Yes |
| Final handover of the project | 17/04/2026 | R2 | No |